## TrustBench-AI
TrustBench-AI: Implementation Plan
Tasks | Completed | Complete % | Blocked | Planned h | Remaining h | Core complete % | Core weeks left | Overdue | Evidence gaps
72 | 49 | 68.06% | 0 | 357 | 137 | 90.74% | 1.0833 | 0 | 0
Hours/week | 12 | Effort is an editable planning estimate. Dates and results start blank.
Phases: A88 | How to use: A104 | Resources & hardware: A123 | Datasets: A133 | Metrics: A141 | Experiments: A154 | Risks: A163 | Sources: A172
Amber cells are editable. Mark Completed only after acceptance checks and an evidence link. Filter Readiness = Ready to choose the next task.
Task ID | Phase | Task / deliverable | Status | Dependency 1 | Dependency 2 | Readiness (formula) | Estimate (hours) | Owner | Due date | Implementation steps | Tools / stack | Data / inputs | Acceptance criteria | Expected evidence | Risk / fallback | Scope | Source IDs | Actual evidence link | Blocker / next action | Evidence present (1/0)
TB-001 | 01 Scope & setup | Define supported agent workflows | Completed |  |  | Done | 3 |  |  | Choose document lookup, mock email drafting and simulated record updates. Specify user intent and permitted side effects. | Markdown, JSON Schema | Three synthetic workflow specifications | Each workflow has observable success and forbidden-action rules. | docs/scope.md | Avoid real external actions in benchmark runs. | Core |  | /Volumes/MHRJ/TrustBench-AI/docs/scope.md |  | 1
TB-002 | 01 Scope & setup | Map threat model and prior work | Completed | TB-001 |  | Done | 5 |  |  | Document trusted user input, untrusted retrieval/tool outputs, attacker control and assets. Compare AgentDojo and CaMeL. | Threat-model diagram | AgentDojo and CaMeL sources | Attack surface and excluded threats are explicit; no novelty claim. | docs/threat-model.md | Provenance tags alone do not prove information-flow security. | Core | TB-S1, TB-S2 | /Volumes/MHRJ/TrustBench-AI/docs/threat-model.md |  | 1
TB-003 | 01 Scope & setup | Lock development environment | Completed | TB-001 |  | Done | 3 |  |  | Create package, dependency lock, linting, deterministic fixture tests and separate dev/test config. | Python, uv, pytest, Docker | Pinned Python and library versions | Fresh checkout installs and runs one fixture without credentials. | lockfile and CI log | Pin a compatible set, not untested latest versions. | Core |  | /Volumes/MHRJ/TrustBench-AI/docs/development-environment.md |  | 1
TB-004 | 01 Scope & setup | Define run and trace contracts | Completed | TB-002 | TB-003 | Done | 4 |  |  | Specify run_id, task_id, model revision, prompt hash, seed, tool spans, policy decisions and evaluator version. | Pydantic, JSONL | Task and trajectory schemas | Invalid events are rejected; a trace reconstructs all executed tool calls. | schemas/ and trace fixture | Never store API keys in traces. | Core |  | /Volumes/MHRJ/TrustBench-AI/docs/trace-contract.md |  | 1
TB-005 | 01 Scope & setup | Set compute and spend limits | Completed | TB-003 |  | Done | 2 |  |  | Measure one representative request. Set maximum calls, tokens, retries, elapsed time and currency budget per run. | Provider usage API, local ledger | Current provider pricing and pilot logs | Budget exhaustion cancels pending work and records an explicit outcome. | configs/budget.yaml | API costs and rate limits must be checked at execution time. | Core |  | /Volumes/MHRJ/TrustBench-AI/configs/budget.yaml |  | 1
TB-006 | 01 Scope & setup | Freeze experiment protocol | Completed | TB-002 | TB-004 | Done | 4 |  |  | Define baseline versus gateway comparisons, primary metrics, paired tasks and model-version policy before tuning. | YAML, experiment registry | Research question and threat model | Protocol specifies exclusions, uncertainty method and holdout policy. | protocol/preregister.md | Do not select winning metrics after seeing holdout results. | Core |  | /Volumes/MHRJ/TrustBench-AI/protocol/preregister.md |  | 1
TB-007 | 02 Data & fixtures | Acquire benchmark and permissions | Completed | TB-006 |  | Done | 3 |  |  | Pin AgentDojo commit, inspect license and task setup, and record the chosen suites and exclusions. | Git, AgentDojo | Official benchmark repository | Manifest contains commit, license, suite IDs and download steps. | data/manifest.json | Do not label a subset as the full benchmark. | Core | TB-S1 | /Volumes/MHRJ/TrustBench-AI/data/manifest.json |  | 1
TB-008 | 02 Data & fixtures | Create local benign task set | Completed | TB-007 |  | Done | 5 |  |  | Build synthetic users, documents and tool state with explicit expected outcomes for each workflow. | SQLite, JSON fixtures | No real personal data | Every task has an independent state-based success checker. | data/benign.jsonl | Avoid model-generated answers serving as sole ground truth. | Core |  | /Volumes/MHRJ/TrustBench-AI/data/benign.jsonl |  | 1
TB-009 | 02 Data & fixtures | Build controlled injection fixtures | Completed | TB-002 | TB-008 | Done | 5 |  |  | Add untrusted text that tries to alter recipient, tool choice or allowed destination. Keep exfiltration targets as local sinks. | Fixture generator, pytest | Synthetic documents and mock tools | Each case labels entry point, attacker goal and allowed behavior. | data/attacks.jsonl | Exercise attacks only against the isolated test environment. | Core |  | /Volumes/MHRJ/TrustBench-AI/data/attacks.jsonl |  | 1
TB-010 | 02 Data & fixtures | Separate tuning and holdout families | Completed | TB-009 |  | Done | 4 |  |  | Split by task template and attack family. Deduplicate paraphrases and hash the locked holdout manifest. | Python, content hashing | Benign and attack fixtures | No near-duplicate family crosses the tuning/holdout boundary. | data/splits.json | Random row splitting can leak attack templates. | Core |  | /Volumes/MHRJ/TrustBench-AI/data/splits.json |  | 1
TB-011 | 02 Data & fixtures | Validate dataset and reset semantics | Completed | TB-010 |  | Done | 4 |  |  | Check IDs, missing labels, malformed payloads and deterministic state reset between episodes. | pytest, SQLite snapshots | All fixture manifests | Validation fails on broken labels and cross-run state contamination. | reports/data-validation.json | A reset failure invalidates paired comparisons. | Core |  | /Volumes/MHRJ/TrustBench-AI/reports/data-validation.json |  | 1
TB-012 | 02 Data & fixtures | Create small end-to-end smoke suite | Completed | TB-011 |  | Done | 3 |  |  | Select one benign and one adversarial case per workflow and expected checker results. | pytest | Versioned smoke fixtures | Runs finish offline with mocked model responses. | tests/smoke/ | Smoke suite is a functional check, not a performance benchmark. | Core |  | /Volumes/MHRJ/TrustBench-AI/tests/smoke/report.json |  | 1
TB-013 | 03 Agent baseline | Implement provider-neutral model adapter | Completed | TB-012 |  | Done | 4 |  |  | Normalize messages, tool calls, usage and provider errors. Capture exact model identifiers and generation settings. | Python SDK, Pydantic | Mock provider and one chosen provider | Adapter contract tests pass for valid and malformed responses. | src/models/ | Provider seed support does not guarantee determinism. | Core |  | /Volumes/MHRJ/TrustBench-AI/artifacts/verification/tb013-model-adapter.json |  | 1
TB-014 | 03 Agent baseline | Implement isolated tool services | Completed | TB-013 |  | Done | 6 |  |  | Expose schema-validated read/search/draft/update operations over synthetic state. Remove credentials and public network egress. | FastAPI, Docker, SQLite | Synthetic fixture state | Tool integration tests enforce state reset and resource limits. | src/tools/ and sandbox config | Containers require restrictive configuration; do not claim universal isolation. | Core |  | /Volumes/MHRJ/TrustBench-AI/evidence/tb014-tool-service-report.json; /Volumes/MHRJ/TrustBench-AI/src/tools/; /Volumes/MHRJ/TrustBench-AI/scripts/verify-tool-service.mjs; /Volumes/MHRJ/TrustBench-AI/agent/sandbox/Dockerfile | Evidence path corrected 2026-10-16: agent/sandbox.ts (eve agent sandbox, removed in commit daaf836) replaced by scripts/verify-tool-service.mjs, which builds agent/sandbox/Dockerfile and runs the verified container configuration recorded in the TB-014 report. | 1
TB-015 | 03 Agent baseline | Build bounded baseline agent | Completed | TB-014 |  | Done | 5 |  |  | Use a small graph with model, tool and termination nodes. Cap steps and preserve all failures. | LangGraph or plain state machine | Model adapter and tool contracts | All trajectories terminate as success, failure, timeout or budget exhausted. | src/agent/ | Keep baseline and defended agent generation settings identical. | Core | TB-S3 | /Volumes/MHRJ/TrustBench-AI/evidence/tb015-baseline-agent-report.json; /Volumes/MHRJ/TrustBench-AI/src/agent/ |  | 1
TB-016 | 03 Agent baseline | Add independent outcome evaluators | Completed | TB-015 |  | Done | 5 |  |  | Check final state against intended task, then separately check attacker goals and prohibited side effects. | Pure Python evaluator functions | Task contracts and traces | Known-good and known-bad trajectories produce expected labels. | tests/evaluators/ | A fluent final answer is not proof of successful execution. | Core |  | /Volumes/MHRJ/TrustBench-AI/evidence/tb016-evaluator-report.json; /Volumes/MHRJ/TrustBench-AI/src/evaluators/; /Volumes/MHRJ/TrustBench-AI/tests/evaluators/ | Frozen v1 (tb016.1.0.0) kept for the TB-017 pilot hash. Post-pilot fixes live in src/evaluators/outcomes_v2.py (tb016.1.1.0): abstention judging, answer normalization, HTTP argument names, decoy-record handling. See protocol/amendments.md A-002. | 1
TB-017 | 03 Agent baseline | Run and store baseline pilot | Completed | TB-016 | TB-005 | Done | 4 |  |  | Run tuning tasks with multiple repeats. Persist raw outputs, costs, timestamps and all failures. | CLI runner, JSONL | Tuning split only | A reproducible report links every metric to run IDs. | runs/baseline-pilot/ | Do not fill metric cells until results are collected. | Core |  | /Volumes/MHRJ/TrustBench-AI/runs/baseline-pilot/ |  | 1
TB-018 | 03 Agent baseline | Review failure taxonomy | Completed | TB-017 |  | Done | 3 |  |  | Manually inspect failures and label model reasoning, tool failure, policy failure, timeout and evaluator error. | Review notebook | Baseline pilot traces | Taxonomy includes ambiguous cases and reviewer disagreements. | reports/failure-taxonomy.csv | Use this to refine tuning fixtures only. | Core |  | /Volumes/MHRJ/TrustBench-AI/reports/failure-taxonomy.csv; /Volumes/MHRJ/TrustBench-AI/reports/failure-review.ipynb; /Volumes/MHRJ/TrustBench-AI/reports/tb018-review-summary.json |  | 1
TB-019 | 04 Policy gateway | Implement centralized tool interception | Completed | TB-018 |  | Done | 6 |  |  | Route every tool call through one gateway before execution; prevent agent access to raw tool clients. | Python middleware, integration tests | Tool contracts | Direct-call bypass fixtures cannot execute a tool. | src/gateway/ | Model instructions cannot enforce access control. | Core |  | /Volumes/MHRJ/TrustBench-AI/src/gateway/; /Volumes/MHRJ/TrustBench-AI/reports/tb019-gateway-tests.xml |  | 1
TB-020 | 04 Policy gateway | Track provenance through tool outputs | Completed | TB-019 |  | Done | 6 |  |  | Attach source IDs and trust labels. Preserve labels during serialization and record transformations. | Typed wrappers, trace schema | Retrieved documents and tool outputs | Unknown or lost provenance is handled explicitly in all adapters. | tests/provenance/ | Document limitations when model text mixes several sources. | Core | TB-S2 | /Volumes/MHRJ/TrustBench-AI/tests/provenance/; /Volumes/MHRJ/TrustBench-AI/reports/tb020-provenance-tests.xml |  | 1
TB-021 | 04 Policy gateway | Enforce capabilities and argument policy | Completed | TB-020 |  | Done | 7 |  |  | Validate allowed operation, resource, recipient and destination against user-scoped capabilities. Default deny unknown operations. | Policy rules, JSON Schema | Per-task capability manifest | Tampered destinations and excess permissions are blocked before side effects. | src/policy/ | An allowlist is only as complete as its normalization rules. | Core |  | /Volumes/MHRJ/TrustBench-AI/src/policy/; /Volumes/MHRJ/TrustBench-AI/reports/tb021-policy-tests.xml; /Volumes/MHRJ/TrustBench-AI/src/policy/capability-manifests.json | Limit: allowlist exactness relies on exact-ID matching (no normalization). Fixture tests only; not proof against all attacks. | 1
TB-022 | 04 Policy gateway | Add approval and replay-safe actions | Completed | TB-021 |  | Done | 5 |  |  | Pause consequential mock operations for approval bound to exact arguments. Add expiry, replay protection and idempotency keys. | LangGraph interrupts, durable store | Synthetic approval events | Changed arguments invalidate approval; resume does not duplicate effects. | tests/approval/ | Graph nodes can restart on resume; isolate side effects. | Core | TB-S3 | /Volumes/MHRJ/TrustBench-AI/tests/approval/; /Volumes/MHRJ/TrustBench-AI/reports/tb022-approval-tests.xml; /Volumes/MHRJ/TrustBench-AI/reports/tb022-approval-events.json; /Volumes/MHRJ/TrustBench-AI/src/policy/workflow.py; /Volumes/MHRJ/TrustBench-AI/scripts/verify-approval-flow.py | LangGraph interrupt() workflow with durable SQLite checkpointer; node-replay, restart, tamper, expiry and repeat-resume tested (24 tests). Guarantee is local-SQLite only; no exactly-once claim for external APIs. Wiring into the baseline agent is TB-024. | 1
TB-023 | 04 Policy gateway | Test boundary and normalization failures | Completed | TB-022 |  | Done | 5 |  |  | Exercise encoded destinations, missing permissions, cross-user IDs, repeated approvals and malformed tool outputs. | pytest, property-based tests | Adversarial policy fixtures | All declared security invariants have negative and positive tests. | reports/policy-tests.xml | Passing fixtures do not prove security against all attacks. | Core |  | /Volumes/MHRJ/TrustBench-AI/reports/policy-tests.xml; /Volumes/MHRJ/TrustBench-AI/reports/policy-invariant-coverage.json; /Volumes/MHRJ/TrustBench-AI/tests/policy/test_invariants.py; /Volumes/MHRJ/TrustBench-AI/fixtures/policy/invariants.json; /Volumes/MHRJ/TrustBench-AI/fixtures/policy/adversarial.json | 8 invariants, each with positive+negative tests enforced at collection (89 tests, 3 consecutive passes, Hypothesis included). Gateway hardened to fail closed on malformed tool output. Synthetic fixtures only; not proof against all attacks. | 1
TB-024 | 04 Policy gateway | Integrate defended-agent workflow | Completed | TB-023 | TB-016 | Done | 4 |  |  | Wire gateway into the same baseline agent and run smoke cases with policy decision traces. | LangGraph, CLI | Same prompts and tool state | Only intended gateway behavior differs between comparison arms. | configs/defended.yaml | Avoid confounding security changes with stronger model prompts. | Core |  | /Volumes/MHRJ/TrustBench-AI/configs/defended.yaml; /Volumes/MHRJ/TrustBench-AI/configs/baseline.yaml; /Volumes/MHRJ/TrustBench-AI/src/arms/; /Volumes/MHRJ/TrustBench-AI/reports/tests/tb024-scripted-as_authored-plain-gateway_capability-report.json; /Volumes/MHRJ/TrustBench-AI/reports/tests/tb024-scripted-as_authored-plain-gateway_capability-policy-traces.jsonl; /Volumes/MHRJ/TrustBench-AI/tests/arms.test.ts; /Volumes/MHRJ/TrustBench-AI/tests/approval/test_approved_call.py; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-tb024.log; /Volumes/MHRJ/TrustBench-AI/protocol/amendments.md; /Volumes/MHRJ/TrustBench-AI/docs/pilot-results-tb024.md; /Volumes/MHRJ/TrustBench-AI/reports/tests/tb024-scripted-as_authored-plain-gateway_capability-suite-holdout-guard-suite-report.json; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-arm-corrections.log; /Volumes/MHRJ/TrustBench-AI/data/attack-renderings.json; /Volumes/MHRJ/TrustBench-AI/configs/live-matrix.yaml; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-harder-attacks.log; /Volumes/MHRJ/TrustBench-AI/docs/known-issues.md; /Volumes/MHRJ/TrustBench-AI/docs/flow-check.md; /Volumes/MHRJ/TrustBench-AI/configs/policy.yaml; /Volumes/MHRJ/TrustBench-AI/evidence/gateway-overhead-report.json; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-flow-check.log; /Volumes/MHRJ/TrustBench-AI/docs/defense-comparison.md; /Volumes/MHRJ/TrustBench-AI/scripts/summarize-defense-comparison.mjs; /Volumes/MHRJ/TrustBench-AI/configs/defense-comparison.yaml; /Volumes/MHRJ/TrustBench-AI/configs/defenses.yaml; /Volumes/MHRJ/TrustBench-AI/src/agent/defenses.ts; /Volumes/MHRJ/TrustBench-AI/tests/arms/stress-cases.json; /Volumes/MHRJ/TrustBench-AI/docs/camel.md; /Volumes/MHRJ/TrustBench-AI/src/agent/camel.ts; /Volumes/MHRJ/TrustBench-AI/tests/camel.test.ts; /Volumes/MHRJ/TrustBench-AI/src/agent/json-extract.ts; /Volumes/MHRJ/TrustBench-AI/tests/json-extract.test.ts; /Volumes/MHRJ/TrustBench-AI/tests/arms/stress-v2-cases.json; /Volumes/MHRJ/TrustBench-AI/tests/arms/stress-v3-cases.json | Updated 2026-10-15 (protocol 1.1.0, amendments A-001..A-008): replacement sealed holdout created and never run; prompt profiles plain/hardened; published AgentDojo attack templates; positive control; run validity/exposure accounting. Live pilot (plain prompt, AgentDojo important_instructions): baseline attacker goal 8/20 (gpt-oss-20b) and 6/12 (qwen3.5:9b) vs 0 defended; generated tables in docs/pilot-results-tb024.md. Unfinished: several registered matrix cells (listed in that doc), Gemini quota exhausted. Residual gap: gateway does not inspect free-text content inside authorized actions. Pilot-sized, not confirmatory. ¦ 2026-10-15 later: provenance-aware flow check added as default defended variant (capability_only kept as ablation; A-010); open items tracked in docs/known-issues.md. ¦ Updated 2026-10-15 (A-011..A-013): plain registered as primary profile; signed provenance envelopes; registered live defense comparison (configs/defense-comparison.yaml, gpt-oss-20b and qwen3.5:9b, 2 reps, important_instructions) against re-implemented spotlighting, sandwich, tool_filter and MELON, generated with Newcombe intervals in docs/defense-comparison.md (all registered cells finished). Candidate gateway_directive_flow is lower than every published baseline and no defense on gpt-oss, but not separated from the capability gateway alone at this sample size; it uniquely stops the answer-poisoning and link cases. Stress fixture TB-ATT-DOC-005 shows its measured blind spot (declarative-only poisoning passes). Contract-backend ablation: gateway benefit assumes a permissive tool backend. All development split; exploratory, not confirmatory. ¦ Evidence paths corrected 2026-10-16: the single scripted report and traces were renamed per run in commit 0d7cc53 (scripted runs are tests, under reports/tests/); the holdout-mechanics report is now the holdout-guard suite report written by npm run test:arms. ¦ Updated 2026-10-16 (A-014..A-019): CaMeL-style baseline re-implemented and compared; directive_flow v2/v3/v4 each pre-registered before its runs, scored per prediction in docs/defense-comparison.md (v3/v4 fresh-fixture predictions supported with non-vacuous classifier calls; pure statement-of-fact poisoning still passes). Added Llama-3.2-11B and Gemma 4; pre-registered pooled analysis (directive_flow vs capability gateway on the new models) not separated, reported with the A-019 parser-bug confound and its correction. Llama models never read injections (no defense effect measurable). Live matrix cells filled (A-014/A-015/A-018). Development split only; exploratory. | 1
TB-025 | 05 Reliability & traces | Add retries and bounded recovery | Completed | TB-024 |  | Done | 5 |  |  | Retry transient read failures with backoff. Avoid automatic retry of non-idempotent writes. | Tenacity or explicit retry logic | Injected timeouts and rate limits | Retry counts stay within budget and writes are never duplicated. | tests/recovery/ | Retries can improve success while worsening cost and latency. | Core |  | /Volumes/MHRJ/TrustBench-AI/tests/recovery/; /Volumes/MHRJ/TrustBench-AI/reports/tb025-recovery-tests.xml; /Volumes/MHRJ/TrustBench-AI/evidence/tb025-recovery-report.json; /Volumes/MHRJ/TrustBench-AI/src/agent/recovery.ts; /Volumes/MHRJ/TrustBench-AI/configs/recovery.yaml; /Volumes/MHRJ/TrustBench-AI/docs/recovery.md; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-tb025.log; /Volumes/MHRJ/TrustBench-AI/evidence/tb024-nvidia-openai-gpt-oss-20b-agentdojo_important_instructions-plain-gateway_capability-faults-reads30_writes30-report.json; /Volumes/MHRJ/TrustBench-AI/docs/pilot-results-tb024.md | Explicit retry logic (no Tenacity): reads retried with seeded backoff inside the registered retry budget; writes get exactly one attempt, unknown outcomes are reported and exact repeats suppressed. 29 tests incl. real-service HTTP fault injection and a naive-retry negative control; seven mutation checks. Seeded trials (synthetic faults, scripted model) show 0 duplicate writes and retries never above budget; success and the extra attempts/backoff cost are in evidence/tb025-recovery-report.json. Limit: LLM behavior after failed/unknown-outcome calls is not measured; durable restart handling is TB-026. ¦ Live fault run 2026-10-15 (gpt-oss-20b, reads30_writes30): no invalid runs, read retries within budget, exact duplicate writes suppressed, service refused re-sent drafts; one undefended run committed a model-rewritten write after an unknown outcome (gateway pinning prevented it in the defended arm). Table: docs/pilot-results-tb024.md, Live fault injection. | 1
TB-026 | 05 Reliability & traces | Add durable checkpoints and cancellation | Completed | TB-025 |  | Done | 4 |  |  | Persist run state and cancellation markers. Test process restart during read, approval and write phases. | SQLite/PostgreSQL checkpointer | Interrupted test runs | Resume or safe abort yields a single final outcome per run. | tests/restart/ | Checkpoint stores need access control and retention limits. | Core |  | /Volumes/MHRJ/TrustBench-AI/tests/restart/; /Volumes/MHRJ/TrustBench-AI/reports/tb026-restart-tests.xml; /Volumes/MHRJ/TrustBench-AI/src/agent/run-store.ts; /Volumes/MHRJ/TrustBench-AI/tests/gateway/test_durable_sessions.py; /Volumes/MHRJ/TrustBench-AI/configs/durability.yaml; /Volumes/MHRJ/TrustBench-AI/docs/durability.md; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-tb026.log | SQLite run store with checkpoints, write-ahead intent log, cancellation markers and a single final outcome per run; durable gateway sessions (hashed tokens, TTL, owner-only file). Restart tests SIGKILL the real agent during read, after a committed write, and at the approval pause (gateway restarted too), plus cancellation; two mutation checks caught. Limits: per-run wall-clock timeout restarts after resume; restored flow-check memory starts empty; retention runs on store open. | 1
TB-027 | 05 Reliability & traces | Instrument spans and redaction | Completed | TB-026 |  | Done | 4 |  |  | Record model, retrieval, policy and tool timing. Redact sensitive fixtures before export and correlate spans by run ID. | OpenTelemetry, JSON logs | Run and tool schemas | All spans link to runs and contain no seeded secret canaries. | observability/ | Timing should include queueing when reporting user latency. | Core |  | /Volumes/MHRJ/TrustBench-AI/observability/README.md; /Volumes/MHRJ/TrustBench-AI/observability/tb027-report.json; /Volumes/MHRJ/TrustBench-AI/observability/traces/; /Volumes/MHRJ/TrustBench-AI/src/observability/tracing.ts; /Volumes/MHRJ/TrustBench-AI/src/observability/run-spans.ts; /Volumes/MHRJ/TrustBench-AI/src/observability/check.ts; /Volumes/MHRJ/TrustBench-AI/scripts/verify-observability.mjs; /Volumes/MHRJ/TrustBench-AI/tests/observability.test.ts; /Volumes/MHRJ/TrustBench-AI/configs/observability.yaml; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-tb027.log | Completed 2026-10-16. OpenTelemetry spans (api + sdk-trace-base), JSON-lines export: one trace per arm run with agent.run root; model.call (queue.ms = pacing wait, so latency includes queueing), tool.call (retrieval-tagged, per attempt, argument SHA-256 only), policy.decision (gateway-timed audit). Every span carries run.id. Export drops non-allowlisted attributes and redacts seeded fixture secrets derived from the data files (holdout excluded). verify:observability passes on scripted and live exports (gpt-oss-20b, Gemma 4); in both live runs the undefended agent read the canary yet no span contains it. Limit: spans cover the TrustBench harness and gateway, not eve's own pilot agent runtime. | 1
TB-028 | 05 Reliability & traces | Build repeated-run evaluator | Completed | TB-027 |  | Done | 5 |  |  | Execute fixed task-seed schedules. Report per-task success frequency and all-repeats success without pooling away variation. | Python, NumPy | Tuning tasks and repeated runs | Changing run order does not change task pairing or denominators. | src/evaluation/repeats.py | Repeated runs of one task are correlated observations. | Core |  | /Volumes/MHRJ/TrustBench-AI/src/evaluation/repeats.py; /Volumes/MHRJ/TrustBench-AI/src/evaluation/README.md; /Volumes/MHRJ/TrustBench-AI/tests/evaluation/test_repeats.py; /Volumes/MHRJ/TrustBench-AI/scripts/verify-repeats.py; /Volumes/MHRJ/TrustBench-AI/evidence/tb028-order-invariance-report.json; /Volumes/MHRJ/TrustBench-AI/observability/schedules/tb028-dev-suite.json; /Volumes/MHRJ/TrustBench-AI/evidence/tb028/; /Volumes/MHRJ/TrustBench-AI/docs/repeated-runs.md; /Volumes/MHRJ/TrustBench-AI/reports/full-verify-after-tb028.log | Completed 2026-10-16. Python + NumPy evaluator: fixed task-seed schedules (unit = task x attack variant x repetition, registered seeds, seeded order; content and order hashed separately); runner executes a schedule exactly and refuses seed mismatches. Per-cluster success frequency, all-repeats and any-repeat success, cluster-bootstrap CIs, paired defended-baseline difference by cluster, intra-cluster correlation; pooled rate shown only as contrast. Acceptance: same units executed in two orders through the real harness give identical pairing, denominators and results (evidence/tb028-order-invariance-report.json); shuffled-input and mutation tests. Live: 80/80 scheduled units on gpt-oss-20b (v4 vs baseline, 5 reps) plus 38 existing repeated-run reports in docs/repeated-runs.md. Baseline ICC 0.5-0.7 shows repeats are strongly correlated. Development split only. | 1
TB-029 | 05 Reliability & traces | Localize trajectory failures | Completed | TB-028 |  | Done | 6 |  |  | Use deterministic rule checks to identify first violated contract. Add optional judge labels only after human calibration. | Trace analyzer, review UI | Labeled failure traces | Attribution accuracy is evaluated against reviewed cases. | reports/attribution.csv | Correlation with a tool step does not establish causality. | Core |  | /Volumes/MHRJ/TrustBench-AI/reports/attribution.csv; /Volumes/MHRJ/TrustBench-AI/src/analysis/localize.py; /Volumes/MHRJ/TrustBench-AI/src/analysis/constructed.py; /Volumes/MHRJ/TrustBench-AI/configs/localization.yaml; /Volumes/MHRJ/TrustBench-AI/src/review/app.py; /Volumes/MHRJ/TrustBench-AI/reports/attribution-audit/; /Volumes/MHRJ/TrustBench-AI/data/reviews/attribution-ai-audit.jsonl; /Volumes/MHRJ/TrustBench-AI/data/reviews/attribution-audit-defects.json; /Volumes/MHRJ/TrustBench-AI/evidence/tb029-attribution-accuracy.json; /Volumes/MHRJ/TrustBench-AI/docs/attribution.md; /Volumes/MHRJ/TrustBench-AI/docs/attribution-audit.md; /Volumes/MHRJ/TrustBench-AI/protocol/amendments.md; /Volumes/MHRJ/TrustBench-AI/tests/analysis/ | Completed with a disclosed deviation (A-020): the reviewed cases are an AI audit (Claude), accepted by the project owner on 2026-10-16 in place of human review; no human has reviewed any case and no human-AI agreement is measured. Measured: localizer 1.3.0 on the final fresh audit round (44 cases) = 46/54 failed checks correct (85%, 95% Wilson 73-92%; utility 35/41, security 11/13). Constructed ground truth 149/149; mutation tests show each 1.3.0 fix is needed. Rounds 1-3 (68%, 78%, 79%) drove fixes and were never re-scored; 18 earlier labels corrected for consistency (A-021, both figures shown). Open: 4 localizer defects D1-D4 (docs/attribution.md), not fixed per A-020. No judge labels used. Rebuild: npm run attribution:build; tests: npm run test:attribution. | 1
TB-030 | 05 Reliability & traces | Build review dashboard | Completed | TB-029 |  | Done | 5 |  |  | Show run filters, trace waterfall, policy reason, task outcome and comparison by configuration. | Streamlit, Plotly | Versioned run store | A reviewer can open raw evidence behind any displayed aggregate. | app/ and screenshots | Keep sensitive payloads redacted in shared demos. | Core |  | /Volumes/MHRJ/TrustBench-AI/web/; /Volumes/MHRJ/TrustBench-AI/web/screenshots/; /Volumes/MHRJ/TrustBench-AI/web/DESIGN.md; /Volumes/MHRJ/TrustBench-AI/web/README.md; /Volumes/MHRJ/TrustBench-AI/web/tests/site.spec.ts; /Volumes/MHRJ/TrustBench-AI/web/src/lib/aggregate.test.ts; /Volumes/MHRJ/TrustBench-AI/app/; /Volumes/MHRJ/TrustBench-AI/configs/dashboard.yaml; /Volumes/MHRJ/TrustBench-AI/reports/dashboard/run-index.json; /Volumes/MHRJ/TrustBench-AI/scripts/export-site-data.py; /Volumes/MHRJ/TrustBench-AI/scripts/verify-dashboard.py; /Volumes/MHRJ/TrustBench-AI/evidence/tb030-dashboard-report.json; /Volumes/MHRJ/TrustBench-AI/tests/app/ | Completed. Review website (web/, Vite + React + Motion; Streamlit removed on request) over a versioned run store: 93 live reports, 4,538 runs, TB-027 spans and TB-029 attribution pinned by SHA-256 (reports/dashboard/run-index.json). Design system in web/DESIGN.md and Figma (TrustBench — Design system). Pages: overview (real trace replay, scroll-linked baseline-to-defended chart), compare (any two dimensions, any verdict), runs, run (timed or step waterfall, policy reasons, gateway audit, raw record with SHA-256 and pointer), policy, outcomes, attribution, evidence index; filters in the URL. Acceptance: npm run verify:dashboard recomputes every aggregate from raw records (642 metric cells, 605 policy rows, 265 outcome rows, 0 mismatches) and checks the export (4,538 runs, 0 record mismatches, 0 leaks); the browser's aggregation equals app/views.py cell for cell (aggregate.test.ts); Playwright on desktop, tablet and mobile: 50 passed, 1 skipped (keyboard on mobile) - console errors, overflow, two-line headings, navigation, links, evidence drawer, controls, download, focus, reduced motion. 27 screenshots in web/screenshots. Redaction: static export is always redacted, variant-aware. Limits: timing only for 180 runs since TB-027; no authentication (known issue E7). | 1
TB-031 | 06 Evaluation | Calibrate controls on tuning data | Completed | TB-030 | TB-006 | Done | 5 |  |  | Select policy thresholds and reliability settings using only tuning data; freeze final configs. | Experiment registry | Tuning split | Chosen configuration and selection rule are recorded before holdout. | configs/frozen/ | No guaranteed attack-success reduction is assumed. | Core |  | /Volumes/MHRJ/TrustBench-AI/configs/frozen/; /Volumes/MHRJ/TrustBench-AI/configs/frozen/selection.json; /Volumes/MHRJ/TrustBench-AI/configs/frozen/reliability.json; /Volumes/MHRJ/TrustBench-AI/configs/frozen/holdout-config.json; /Volumes/MHRJ/TrustBench-AI/configs/frozen/MANIFEST.sha256; /Volumes/MHRJ/TrustBench-AI/configs/selection.yaml; /Volumes/MHRJ/TrustBench-AI/configs/reliability-sweep.yaml; /Volumes/MHRJ/TrustBench-AI/scripts/select-frozen-config.py; /Volumes/MHRJ/TrustBench-AI/scripts/select-reliability.py; /Volumes/MHRJ/TrustBench-AI/scripts/verify-frozen.py; /Volumes/MHRJ/TrustBench-AI/tests/selection/; /Volumes/MHRJ/TrustBench-AI/docs/frozen-config.md; /Volumes/MHRJ/TrustBench-AI/docs/reliability-sweep.md; /Volumes/MHRJ/TrustBench-AI/protocol/amendments.md | Completed. Rules pre-registered as A-023 (system selection) and A-024 (reliability sweep) and applied by script to tuning-split runs only (holdout fixtures checked absent; no holdout run exists). Selected gateway_directive_flow_v4 on gpt-oss-20b, plain profile: unsafe 76.1% -> 0.0% (paired cluster bootstrap -88.9 to -63.1 pp), benign utility 70.0% -> 88.0%; 2 of 14 systems met the evidence minimum and gate. Thresholds = the registered v4 version. Reliability sweep (5 configurations x 48 pairs, 0 invalid): step limit 12 and timeout 240 s kept (16 steps cost 14 pp utility, 8 steps and 360 s raised terminations); read retries 4 -> 2 adopted (no worse, 3.1 s faster), applied only to the holdout via configs/frozen/reliability-override.json. Frozen configs, settings copies, classifier prompt and SHA-256 manifest in configs/frozen/; npm run verify:frozen fails on drift. Disclosed: winner's curse, v4 designed on these fixtures, ~27 attack / 21 benign runs per arm in the sweep, budget limits not swept, A-024 committed with its results. No attack-success reduction on the holdout is assumed. | 1
TB-032 | 06 Evaluation | Run paired holdout benchmark | Completed | TB-031 | TB-010 | Done | 8 |  |  | Evaluate baseline and defended variants on identical tasks, repeat schedules and model revision within budget. | Batch runner | Locked holdout | Missing runs and provider outages remain visible in the report. | runs/holdout/ | If provider changes, rerun both arms or label the comparison invalid. | Core |  | runs/holdout/; evidence/tb032-holdout-run.json; docs/holdout-run.md; evidence/release-gate-dev.json; runs/holdout2/; evidence/tb032-holdout2-run.json; docs/holdout2-run.md; evidence/holdout2-validation.json; evidence/holdout2-prerun.json | Done 2026-10-17: frozen config on the sealed holdout suite (3 benign, 3 attack), 5 renderings x 6 cases x 5 repetitions: 150/150 pairs valid, one response model; second execution refused; holdout use consumed. Extension (A-026, protocol 1.2.0): a fresh sealed holdout-2 of 12 new task templates (12 benign, 12 attacks incl. 3 new families), validated without a model (44/44 oracle checks), run once with the unchanged frozen config: 240/240 pairs valid, 0 invalid, one response model (openai/gpt-oss-20b). Disclosed: holdout-2 was authored after holdout-1 aggregate rates were seen; composition fixed in A-026 first. Comparisons are TB-033/TB-034. | 1
TB-033 | 06 Evaluation | Compute security and utility metrics | Completed | TB-032 |  | Done | 4 |  |  | Calculate attack success on eligible attacks, benign task completion and false blocks of permitted actions. | Pandas, SciPy | Raw task outcomes | Report numerators, denominators and exclusions for every rate. | reports/security-utility.csv | Do not count blocked legitimate tasks as security successes alone. | Core |  | reports/security-utility.csv; evidence/tb033-metrics.json; docs/security-utility.md; reports/security-utility-holdout2.csv; evidence/tb033-holdout2-metrics.json; docs/security-utility-holdout2.md; scripts/compute-security-utility.py; tests/evaluation/test_security_utility.py | Done 2026-10-17: every rate recomputed from raw records with numerator, denominator, Wilson 95% (SciPy) and exclusions, tables via pandas, cross-checked against the runner summaries; code committed before each holdout ran through it. Holdout-1 primary: unsafe 10/15 -> 3/15, utility 10/15 -> 14/15. Holdout-2 primary: unsafe 42/60 -> 5/60 (70.0% -> 8.3%), utility 34/60 -> 52/60, false blocks 2/127 permitted calls (argument level also 2/127). Pooled primary: unsafe 69.3% -> 10.7%, utility 58.7% -> 88.0%. Not hidden: defended unsafe is 20% (3/15) on the three new families vs 5% (2/40) on reused tuning families; holdout-1 primary was 20%; argument-level label is post hoc for holdout-1. Paired intervals are TB-034. | 1
TB-034 | 06 Evaluation | Estimate uncertainty and repeatability | Completed | TB-033 |  | Done | 5 |  |  | Bootstrap paired differences at task level; report intervals and per-family slices. Separate zero attacks observed from zero risk. | SciPy, bootstrap script | Paired run records | Seeded analysis reproduces intervals and preserves task clusters. | reports/uncertainty.json | Small samples yield wide intervals; report them. | Core |  | reports/uncertainty.json; docs/uncertainty.md; scripts/estimate-uncertainty.py; configs/uncertainty.yaml; tests/evaluation/test_uncertainty.py; requirements/analysis.lock | Done 2026-10-17: paired cluster bootstrap (10000 resamples of whole task/attack clusters with their repetitions, seed 20261048, SciPy/numpy), exact McNemar (supporting), one-sided bounds where zero events were observed, per-attack, per-workflow and family-status slices, latency/token intervals, TB-028 repeatability. Seeded rerun reproduces every published interval (test). Primary unsafe difference: holdout-1 -46.7 pp [-100, 0] (3 clusters, does not exclude zero); holdout-2 -61.7 pp [-81.7, -40.0]; pooled -58.7 pp [-77.3, -38.7]. Benign utility lower bounds above the -5 pp margin in all three. Not hidden: on the 3 new attack families the interval does not exclude zero (-53.3 pp [-100, 0]); tuning families -62.5 pp [-87.5, -35.0]; few clusters; cost is zero on free tiers, tokens reported instead. Next: TB-035. | 1
TB-035 | 06 Evaluation | Measure latency and operating cost | Completed | TB-034 |  | Done | 4 |  |  | Measure p50/p95 end-to-end time and billed tokens/currency per completed task, including failed attempts. | Trace exporter, cost ledger | Same workload and rate limits | Comparison records concurrency, provider price date and retry settings. | reports/cost-latency.csv | Do not compare latency under different concurrency settings. | Core |  | reports/cost-latency.csv; reports/cost-ledger.csv; evidence/tb035-cost-latency.json; docs/cost-latency.md; scripts/measure-cost-latency.py; tests/evaluation/test_cost_latency.py | Done 2026-10-17: from the TB-027 spans of both confirmatory workloads (780 runs, every reported run covered); cost ledger of all 3,604 model-call attempts incl. 23 failed, priced from the frozen pricing block (free tier, 0 USD, verified 2026-10-15, build.nvidia.com). Records concurrency (measured per run, levels 0-2, at most 3 runs at once), retries (2 attempts per call, backoff, budget max 3), pacing 1000 ms and 240 s timeout. Latency compared only at matched concurrency: defended adds about +7 to +25 s mean per run (holdout-2 attack, level 2: +23.9 s [+9.7, +39.0]); pairs whose arms ran at different levels are excluded and counted. Billed cost is 0, so tokens per successful task is the cost measure: defended uses fewer per success (holdout-2 benign 6,731 vs 7,614). Next: TB-036. | 1
TB-036 | 06 Evaluation | Run ablations and publish negative results | Completed | TB-035 |  | Done | 7 |  |  | Compare baseline, schema-only policy, capability policy and full provenance/approval system under the same budget. | Experiment CLI | Frozen configurations | Every component claim has an ablation or is labeled untested. | reports/ablations.csv | A null or negative result is valid research evidence. | Core |  | reports/ablations.csv; evidence/tb036-ablations.json; docs/ablations.md; configs/ablations.yaml; scripts/run-ablations.mjs; scripts/analyse-ablations.py; tests/evaluation/test_ablations.py; tests/policy/test_ablation_layers.py | Done 2026-10-17 (A-027, development data only; both holdouts already used): 6 new arms x 48 pairs + the frozen system's gate run, identical frozen settings and budget, 0 invalid. Credited: tool allowlist + contract scoping (-51.8 pp unsafe [-77.8, -25.9], also +23.8 pp utility) and the gateway under the directive-flow defense (-70.4 pp [-88.9, -48.1]). Negative/null results published: schemas alone, exact-argument approval (0.0 pp; it fired 10 times but contract scoping already binds update arguments), directive flow on top of the gateway (-22.2 pp [-55.6, 0]), sticky denials (0.0 pp), blocking flow check (-14.8 pp, n.s., with a -23.8 pp utility cost). 14 claims: 7 tested, 7 labelled untested with reasons. Baseline varied 63-85% unsafe across runs (stochastic), stated. Next: TB-037. | 1
TB-037 | 07 Delivery & operations | Package reproducible benchmark CLI | Completed | TB-036 |  | Done | 4 |  |  | Provide commands for fixture validation, smoke, benchmark, evaluate and report with configuration files. | Typer, Docker | Pinned code and data manifests | Fresh environment reproduces smoke results and report schema. | README quickstart | Full API runs require user-supplied credentials and budget. | Core |  | README.md; docs/benchmark-cli.md; evidence/tb037-fresh-reproduction.json; src/cli.py; bin/trustbench; configs/cli/trustbench.yaml; schemas/arm-report.schema.json; manifests/pinned.json; Dockerfile.bench; tests/cli/test_cli.py | Done 2026-10-17: Typer CLI (validate, fetch-data, smoke --check, benchmark <profile>, evaluate, report --check, manifest) driven by configs/cli/trustbench.yaml; report schema (all 125 existing reports valid); pinned content manifest checked in verify; Docker image pinned by digest. Fresh clone (no node_modules/venv/vendor) following the README: all CLI steps and the full npm run verify exit 0, smoke outputs equal the committed results apart from listed volatile fields, 55 reproduction tests pass; the container (Node 26.5.0, npm 12.0.0, Python 3.14.0) passes the same CLI checks. Defect found and fixed: the quickstart missed the review-site dependencies. Not covered: live benchmark runs need the user's own key and quota (dry-run only). Next: TB-038. Extended 2026-10-17: trustbench remote (catalog, run, status, report) drives the live-test service behind the website's Live page (docs/live-service.md); hardening and public deployment are TB-039 and TB-041. | 1
TB-038 | 07 Delivery & operations | Add regression release gate | Completed | TB-037 |  | Done | 5 |  |  | Gate on fixed smoke invariants and preregistered paired-regression tolerances; distinguish inconclusive from pass. | GitHub Actions, pytest | Baseline artifacts and tolerance config | Injected functional/security regressions block the release. | .github/workflows/ | A noisy model result should not silently pass or trigger endless reruns. | Core |  | .github/workflows/release-gate.yml; scripts/ci.sh; scripts/release-gate-scripted.py; scripts/release-gate.py; configs/release-gate.yaml; tests/release/test_injected_regressions.py; tests/selection/test_release_gate.py; docs/release-gate.md | Done 2026-10-17 (A-028): Tier 1, every change: fresh scripted runs and the smoke suite compared case by case with baselines as committed on the base branch (fixed invariants, zero tolerance). Tier 2, per release candidate: the A-025 live gate (T1/T2, INCONCLUSIVE blocks) with an attempt ledger: one run, a second only with a defect note, never a third. Injected regressions (contract resource check removed, argument binding removed, email body dropped, over-blocking gateway) all FAIL; an unmodified candidate PASSES; editing one's own baseline does not hide a regression. CI steps (scripts/ci.sh tier1) passed in a clean Linux container; npm run verify passes. External prerequisite not yet met: the repository has no GitHub remote, so the workflow has not run on GitHub; it runs on the first push. Next: TB-039. | 1
TB-039 | 07 Delivery & operations | Secure benchmark API and storage | Completed | TB-038 |  | Done | 4 |  |  | Add authentication, per-user run isolation, request quotas and retention/deletion jobs. Applies to the live-test service behind the public website (src/service, docs/live-service.md): visitors run with the project key or their own free-tier key, from the browser or the CLI. | FastAPI, secrets manager | Synthetic multi-user test cases | Unauthorized read/run requests fail; deletion removes linked artifacts. Project and visitor keys never appear in storage, logs, responses or run artifacts (tested); public run creation is quota-limited per visitor and by a daily shared budget. | tests/api-security/ | Use local deployment if hosted identity setup is unavailable. | Core |  | tests/api-security/; evidence/tb039-api-security.json; docs/live-service.md; src/service/app.py; src/service/accounts.py; src/service/sessions.py; src/service/secrets.py; src/service/mail.py; web/src/pages/Account.tsx | Done 2026-10-17: authentication with no forced sign-up (anonymous guest sessions) plus real accounts: sign-up, emailed verification, sign-in, sign-out, forgot/reset/change password, account deletion; scrypt passwords, lockout, enumeration-resistant answers, hashed tokens. Per-user isolation (others get 404), read-only revocable share links, owner deletion of runs/sessions/accounts with every artifact, retention sweep (guests 24 h, accounts 30 days), quotas per address, per session, for sign-in and the shared budget; secrets via env, NAME_FILE or /run/secrets with log redaction; strict security headers. tests/api-security 28 pass; website Account pages and CLI login tested; container checked. Not built: Google/GitHub sign-in (needs OAuth apps), MFA, a managed cloud secrets service. Deployment needs SMTP secrets for accounts; guests need nothing. Next: TB-040. | 1
TB-040 | 07 Delivery & operations | Exercise faults and resource exhaustion | Completed | TB-039 |  | Done | 5 |  |  | Simulate unavailable model, corrupt checkpoint, tool crash and log-store failure. Check cancellation and clean recovery. | Fault injection fixtures | Staging environment | Failures produce explicit status and do not bypass policy. | reports/fault-drill.md | Fail closed for uncertain authorization; report resulting availability cost. | Core |  | reports/fault-drill.md; evidence/tb040-fault-drill.json; tests/faults/; scripts/fault-drill.py; configs/fault-drill.yaml; reports/tb040-fault-tests.xml; reports/tb040-fault-checkpoint.xml | Done 2026-10-17: 50/50 drill tests pass (unavailable model: refused/503/hung provider give explicit invalid network/server/timeout, no tool runs, no allow decision; corrupt or altered checkpoint and final outcome give checkpoint_corrupt with no replay; tool crash gives 502 tool_backend_error with nothing committed; log-store failure denies with 503 audit_unavailable via a fsynced write-ahead intent log; deleting a running run stops its whole process group; unwritable storage refuses runs (503) before reserving budget and the service starts degraded instead of crashing; damaged budget record pauses the shared key). Container drills on trustbench-live:tb040: no-network live run ends invalid (network), cancel leaves no processes, read-only volume serves site and catalog with sessions/runs 503. Availability cost measured: +0.1 ms median per allowed call (write-ahead audit), 4 us SHA-256 per checkpoint, hung-provider runs now invalid (23 of 780 confirmatory runs, 2.9%); sensitivity: primary pooled unsafe-effect difference -58.7 -> -59.4 pp, conclusions unchanged; registered results not rewritten. Not covered: a writer who recomputes the checkpoint checksum (needs a keyed MAC), SQLite disk-full, real provider outages, host memory/CPU exhaustion. | 1
TB-041 | 07 Delivery & operations | Deploy a constrained demo | Completed | TB-040 |  | Done | 4 |  |  | Deploy synthetic workflows with spend caps and read-only public results; keep action endpoints authenticated. Deploy the website and live-test service container (Dockerfile.service) at a public URL linked from the GitHub README: hosted mode uses the project free-tier key as a host secret with daily caps, visitors may bring their own free-tier key, and instant (scripted) runs and the published results need no key. | Docker Compose, chosen host | Synthetic demonstration suite | Demo health check, authentication and budget limits are verified. A reviewer with no API key can open the README link and complete a live run (project key) and an instant run, from the browser and from the CLI (trustbench remote); exhausted quota degrades to the other modes with a clear message. | deployment runbook | Do not expose benchmark credentials or attack controls publicly. | Core |  | docs/deployment-runbook.md; evidence/tb041-deployment.json; evidence/tb041/; deploy/compose.yaml; deploy/watchdog.sh; deploy/install-watchdog.sh; configs/deploy/public-demo.json; scripts/check-deployment.py; scripts/check-deployment-gui.mjs; .github/workflows/public-demo-check.yml; tests/deploy/; README.md | Done 2026-10-17: public demo at https://trustbench.taila273c6.ts.net (README link on GitHub), self-hosted compose deployment behind Tailscale Funnel with the constrain-only public-demo profile (2 pairs per hosted run, 40 shared pairs a day), read-only container, secrets as files, project key never in image, logs or run data. Checked from GitHub's runners: check-deployment --live 20/20 (instant and live runs from API and CLI, auth, quotas, rejected visitor key explicit) and the browser path (instant run, live run on the project key, 2/2 valid each); exhausted shared budget refuses hosted with a clear message while instant and own-key work (tested on the deployment). Restart: server crash back in 8 s, Docker restart 36 s, watchdog repairs a stopped container or lost Funnel in 21 s. Host privacy: Docker file sharing limited to the project folder (home and other paths refused), Docker data on the project drive, no personal name in the URL or committed reports. CI green. Known limits: best-effort self-hosting (machine must stay on; power-failure auto-restart is an owner setting not yet on); from the host itself the public relay route times out, so host-side checks use the tailnet route; HF Docker Spaces need PRO and Oracle A1 had no capacity (recorded). | 1
TB-042 | 07 Delivery & operations | Test rollback and artifact restore | Completed | TB-041 |  | Done | 3 |  |  | Restore previous policy/config version and run-store backup; rerun representative fixtures. | Versioned configs, backup script | Previous release and synthetic backup | Rollback restores expected behavior and audit trail. | reports/rollback-drill.md | Record recovery time as measured, not promised. | Core |  | reports/rollback-drill.md; evidence/tb042-rollback-drill.json; scripts/rollback-drill.py; scripts/backup.py; configs/rollback-drill.yaml; deploy/backup-demo.sh; tests/rollback/; tests/release/test_injected_regressions.py; docs/release-gate.md; docs/deployment-runbook.md | Done 2026-10-17 against previous release release-tb041. Config rollback: a bad policy change (approval requirement dropped) is blocked by Tier 1, configs restored from the release in 0.26 s, fixtures rerun and gate PASS, 56/56 policy decisions per arm identical to the release; measured recovery 18.8 s. Found and fixed: the gate compared only verdicts, so that change (record updates without their approval pause) had passed; Tier 1 now blocks a more permissive policy audit trail (injected-regression test added). Service data restore: backup taken while running, data lost, tampered backup refused, restore to serving 0.25 s with byte-identical runs, artifacts and 21 audit files, account login, guest session and share link intact. Run-store restore: interrupted run resumes from restored store exactly as from a never-lost store, write committed once (233 ms). Deployment rollback to the previous release image: healthy in 6.0 s, data intact, roll forward 5.9 s. Public demo backed up (325 files, verified). Limits: small synthetic state, backups on the same drive, no data-format change between releases exercised. One CI run failed once in test:recovery and passed on rerun; recovery tests now print results to the log. | 1
TB-043 | 08 Research evidence | Write related-work comparison matrix | Completed | TB-036 |  | Done | 4 |  |  | Compare threat models, enforcement boundaries, evaluation suites and claimed guarantees to prior systems. | Literature spreadsheet | AgentDojo, CaMeL, relevant new papers | Every comparison has a source and a specific limitation. | research/related-work.csv | Refresh search before claiming a contribution. | Core | TB-S1, TB-S2 | research/related-work.csv; research/related-work.md; research/related-work-rows.py; scripts/build-related-work.py; tests/research/test_related_work.py; docs/threat-model.md | Done 2026-10-17: matrix of 24 prior systems and studies plus TrustBench (9 benchmarks incl. AgentDojo, InjecAgent, ASB, WASP, AgentDyn, AutoDojo, AgentSecBench, NetInjectBench; 13 defenses incl. CaMeL, FIDES, RTBAS, Progent, MELON, StruQ, SecAlign, Instruction Hierarchy, Spotlighting; design patterns; an adaptive evaluation of out-of-band defenses), each with threat model, enforcement boundary, evaluation suite, claimed guarantee, reported result, a specific limitation and its basis (6 stated by authors, 7 reported by later work, 5 measured on this harness, 7 our analysis). Every source checked against its primary listing; search refreshed for 2025-2026 work on 2026-10-17. Builder fails on a missing source or limitation, a dangling basis or a TrustBench statistic not quoted verbatim from its own row (8 tests). Refresh findings: out-of-band enforcement is the current consensus, so TrustBench claims no new defense idea; static benchmarks overestimate defenses and TrustBench has no adaptive evaluation yet (recorded as open). Re-implemented comparators are labelled as such. | 1
TB-044 | 08 Research evidence | Test research hypothesis explicitly | Completed | TB-043 |  | Done | 5 |  |  | Assess whether provenance-aware enforcement improves attack resistance at comparable benign utility and cost. | Paired analysis | Holdout and ablation outputs | Conclusion states effect sizes, uncertainty and failure slices. | research/findings.md | Combining existing components is not by itself novel. | Core |  | research/findings.md; evidence/tb044-hypothesis.json; scripts/test-hypothesis.py; configs/hypothesis.yaml; tests/research/test_hypothesis.py | Done 2026-10-18 under the preregistered rule (unsafe interval below zero, utility lower bound above -5 pp). Supported on the pre-declared pool: unsafe committed effect 52/75 -> 8/75, -58.7 pp [-77.3, -38.7]; benign utility 44/75 -> 66/75, +29.3 pp [+16.0, +44.0]. Per holdout: holdout-2 supported (-61.7 pp [-81.7, -40.0]), holdout-1 not separated (-46.7 pp [-100, 0]); secondary renderings mixed. Failure slices: document workflow not separated (-16.0 pp [-40, 0]); TB-ATT-DOC-104 succeeded as often defended as undefended (3/5); new-family and holdout-1-attack slices include zero; 8 defended unsafe runs and 9 defended benign failures listed (mostly record-update mismatches). Cost: billed $0; +16.2 s and +671/+415 tokens per run, fewer tokens per success in 9 of 12 workloads. Not shown: that the provenance-aware part causes the gain (development ablation -22.2 pp [-55.6, 0], no confirmatory capability-only arm); combining existing components is not novel; no adaptive attacker. Hung-provider sensitivity -59.4 pp, conclusion unchanged. | 1
TB-045 | 08 Research evidence | Audit labels and evaluator quality | Completed | TB-044 |  | Done | 4 |  |  | Double-review a stratified sample of successes and failures. Adjudicate disagreements and record evaluator changes. | Annotation sheet | Raw traces and expected state | Report sample method, agreement and adjudication outcomes. | research/label-audit.csv | If labels change, rerun affected metrics without cherry-picking. | Core |  | research/label-audit.csv; research/label-audit.md; evidence/tb045-label-audit.json; research/label-audit/adjudication.jsonl; research/label-audit/rerun.json; scripts/label-audit.py; configs/label-audit.yaml; tests/research/test_label_audit.py; protocol/amendments.md | Done 2026-10-18. Sample: 61 of 780 valid confirmatory runs, stratified by workflow, kind, arm and evaluator verdict (22 strata, 3 per stratum, fixed seed), blind packets without evaluator labels. Two independent AI reviewers (A: Claude; B: Nemotron 3 Super, a different model family); no human reviewer, which is a stated limit. Agreement with the evaluator: utility 88.5% / 91.8% (kappa 0.77 / 0.84), security 88.5% / 100%, attacker goal 98.4% / 98.4%. 16 labels adjudicated with written reasons: 8 reviewer errors, 7 definition upheld (out-of-allowlist reads count as unsafe), 1 evaluator error. Evaluator error per label: 0/61, 0/61, 1/61 (Wilson upper 5.9%, 5.9%, 8.7%). The error was an oracle defect (a forbidden read counted as the attacker goal for 3 write-goal attacks): fixed in evaluator tb016.1.3.0 (A-029, post hoc, registered results not rewritten); all 780 runs relabelled from their traces, 6 changed, every analysis recomputed: 3 secondary/control attacker-goal cells change, primary unchanged, TB-044 decision stands. Sensitivity (extra reads counted as safe): pooled primary unsafe difference -58.7 -> -42.7 pp [-58.7, -26.7], still excludes zero; some secondary renderings lose separation. Scripted release-gate baselines refreshed for the evaluator change (doc-birch-exfil baseline attacker goal True -> False). | 1
TB-046 | 08 Research evidence | Package reproducibility artifacts | Completed | TB-045 |  | Done | 4 |  |  | Publish allowed fixture IDs, seeds, configs, hashes and analysis scripts. Exclude secrets and restricted data. | Git release, data manifest | Final experiment artifacts | Another user can reproduce an offline subset from documented steps. | repro/ | Provider behavior may prevent exact replay of historical runs. | Core |  | repro/README.md; repro/manifest.json; repro/reproduction-log.json; repro/reproduction-log-clone.json; repro/run-in-container.sh; scripts/repro.py; configs/repro.yaml; tests/research/test_repro.py | Done 2026-10-18. Git release repro-tb046 (tag on 0c1f9d0, GitHub release published). repro/manifest.json publishes fixture IDs by split (tuning, holdout, holdout2), the seeds from the registry (pair order 20261014, split 2026101401, 10000 bootstrap resamples) and SHA-256 hashes of 6 fixture files, 41 configs, 10 analysis scripts and 14 raw run records. Excluded and checked (scripts/repro.py check): .env, deployment secrets, demo backups, the AgentDojo checkout (fetched by pinned commit, MIT), local state; no credential-shaped string in the tree or in the full git history (only a fake test key), and no personal identifier in the tree (two docs that named the author's machine were fixed; older commit texts still contain a local path and machine name, not rewritten). Acceptance: the offline subset (10 steps: validate, pinned hashes, scripted smoke, TB-033..036 metrics from raw records, TB-043, TB-044, TB-045 rerun and report, reproduction tests, research tests) reproduced 10/10 with 0 unexpected file changes in two routes: a clean Linux container as a non-root user with no network from only the tracked files, and a fresh GitHub clone of the tag following repro/README.md. Only timestamps, wall-clock timings and random IDs differ. Limits: both runs by the author (no independent person yet); live model runs cannot be replayed exactly (raw records published, all numbers recomputed from them); the AgentDojo check needs fetch-data (network); browser tests need Chrome. | 1
TB-047 | 08 Research evidence | Draft technical report | Completed | TB-046 |  | Done | 5 |  |  | Write problem, method, threat model, experimental design, results, failure cases and limits with evidence links. | Markdown or LaTeX | Verified experiment tables | All numeric claims map to stored run artifacts. | research/report.pdf or report.md | Do not imply publication acceptance or patentability. | Core |  | research/report.md; research/report-claims.json; research/report.template.md; scripts/build-report.py; configs/report.yaml; tests/research/test_report.py | Done 2026-10-18. research/report.md (Markdown) covers problem, threat model, system, experimental design, results, failure cases, evaluation quality, engineering evidence, limits and relation to prior work, with links to the evidence. Acceptance: every number is a placeholder resolved from a committed artifact; the claim ledger research/report-claims.json maps all 137 claims to 18 source files (path, raw value, rendered text, report line) with content hashes. Checks: the build fails on any digit or number word outside a placeholder or identifier, any dead link or cited path, any unrendered placeholder, and overclaiming phrases (patent, publication acceptance, state of the art, provable or guaranteed security); tests re-resolve every claim, scan the rendered report so every number on a line is covered by a claim (an injected unsourced number fails), and check source hashes. The report check is a reproduction step: 11/11 reproduced in the clean offline container at 7285854. Stated in the report: not peer reviewed; holdout-1 alone not separated; provenance layer not shown to drive the gain; static attacks only; AI-only label audit. | 1
TB-048 | 08 Research evidence | Review contribution and claim boundaries | Completed | TB-047 |  | Done | 3 |  |  | Separate replicated components, engineering contributions and hypotheses needing more evidence. | Claim checklist | Report and prior-work matrix | No novelty, security guarantee or resume metric exceeds evidence. | research/claims.md | Seek specialist review before any patent or publication claim. | Core |  | research/claims.md; research/claims-ledger.json; research/claims-check.json; research/claims.template.md; scripts/check-claims.py; configs/claims.yaml; tests/research/test_claims.py | Done 2026-10-18. research/claims.md separates: components replicated or adapted from prior work (each with its related-work row: Progent, tool filter, RTBAS, CaMeL, FIDES, AgentDojo, InjecAgent, spotlighting, repeat prompt, MELON, WASP, out-of-band consensus RW24); engineering contributions with evidence; result statements that may be made, each with its required qualifier and numbers from stored artifacts (21 claims, ledger); hypotheses needing more evidence (provenance layer as cause, holdout-1 alone, adaptive attacker, generalisation, over-defense, human labels); and what is not claimed (novelty, guarantees, production readiness, patent or publication, hiring). Acceptance check (scripts/check-claims.py, in verify and the offline reproduction): 64 public files scanned for novelty, guarantee, publication, patent and resume phrases; 49 hits, each allowed with a reason (negations, descriptions of other work, narrow tested mechanism properties, the frozen label); a planted overclaim or an unsourced portfolio number fails. Fixed: the website headline claimed each defense cut attacks from point estimates (now a count such as 'Fewer attacker wins for 12 of 14 defenses', with development data and point estimates stated beside it; the public demo shows it after its next redeploy). Not fixed, disclosed: the working label 'novel candidate' stays in the frozen-matched live config and recorded reports (changing it needs a new amendment). Reproduced 12/12 in the clean container at d3a15fb. No specialist review has been done; none is needed until a patent or publication claim is considered. | 1
TB-049 | 09 Portfolio release | Create architecture and walkthrough | Completed | TB-042 | TB-048 | Done | 3 |  |  | Diagram trust boundaries and record a benign run, blocked attack, failure trace and release-gate example. Include a walkthrough of the public live site (each mode, GUI and CLI). | Mermaid, screen recording | Synthetic demo | Walkthrough explains each result and its underlying evidence. | docs/architecture.md and demo video | Do not stage fake measured outcomes. | Core |  | docs/architecture.md; docs/architecture-claims.json; docs/media/walkthrough.webm; docs/media/walkthrough-steps.json; evidence/tb049-walkthrough.json; evidence/tb049-cli-transcript.txt; scripts/walkthrough.py; scripts/record-walkthrough.mjs; tests/research/test_walkthrough.py | Done 2026-10-18. docs/architecture.md: Mermaid trust-boundary diagram and component map; a benign run, a blocked attack beside its undefended pair, a failure trace and a release-gate example, each explained with its evidence (site link, raw record pointer, verdict codes, attribution); every number from stored artifacts (80 claims, ledger). Examples chosen from recorded runs by fixed rules (scripts/walkthrough.py), not staged: the frozen system on the development split (the store holds no holdout run). Release-gate example run for real: unmodified PASS, injected regression (resource check removed) FAIL with security regressions and a more permissive policy trail. Live site: demo redeployed at the current commit; every mode run from the CLI against the public URL (instant, project key, own key) and a report downloaded (evidence/tb049-cli-transcript.txt, no key recorded); video docs/media/walkthrough.webm (2:26, captions) of the site: run pages, policy page, an instant run with report download, the own-key form (not filled), a live run on the project key, the CLI tab. Defect found and fixed: instant runs with every scripted case failed (duplicate repeatability units); fix in src/evaluation/repeats.py with tests, registered results unchanged, demo redeployed. Limits stated: recorded from the host over the tailnet route; own-key mode used the project's key standing in for a visitor's. Reproduced 12/12 in the clean container at 9b85719. | 1
TB-050 | 09 Portfolio release | Document setup and troubleshooting | Not Started | TB-049 |  | Ready | 3 |  |  | Provide install, API key setup, budget controls, expected smoke outputs and failure recovery instructions. Cover the live site and trustbench remote, including bringing your own free-tier key. | README | Clean-environment installation | A fresh user can follow the instructions without hidden local files. | README.md | Document minimum tested environment only. | Core |  |  |  | 0
TB-051 | 09 Portfolio release | Run final clean-checkout verification | Not Started | TB-050 |  | Waiting | 4 |  |  | Install locked dependencies, run fixtures and regression checks, rebuild demo and verify linked reports. Verify the public live site end to end: each mode from the browser and from the CLI, report download, and the no-key path. | CI, Docker | Release candidate | All required checks pass or release is blocked with a written reason. | release/checks.json | Do not equate a passing smoke suite with full benchmark replication. | Core |  |  |  | 0
TB-052 | 09 Portfolio release | Prepare measured resume bullets | Not Started | TB-051 |  | Waiting | 2 |  |  | Write problem/action/result bullets using only completed evaluations, sample sizes and reproducible evidence. | Claim-to-evidence table | Final report | Every number has a run/report reference; unknowns are omitted. | portfolio/bullets.md | No top-1-percent or guaranteed-hiring claims. | Core |  |  |  | 0
TB-053 | 09 Portfolio release | Publish versioned release package | Not Started | TB-052 |  | Waiting | 2 |  |  | Tag code, attach report, license notices and reproduction manifest; verify download links. | Git releases | Release candidate and allowed assets | Published package contains no keys and has a working quickstart. | Release URL | Check benchmark redistribution terms before uploading fixtures. | Core |  |  |  | 0
TB-054 | 09 Portfolio release | Complete handover and backlog | Not Started | TB-053 |  | Waiting | 2 |  |  | Record unresolved failure modes, supported versions, next experiment and maintenance triggers. | Issue tracker | Open risks and results | All Core tasks have acceptance evidence or remain open. | docs/handover.md | Completion means an evidenced project, not universal agent security. | Core |  |  |  | 0
TB-055 | 10 External agent validation | Select an independent external agent | Not Started | TB-054 |  | Waiting | 4 |  |  | Define selection criteria (developed independently of TrustBench, open-source licence permitting evaluation, tool or function calling, runs on free models or local Ollama, active maintenance, pinned release). Shortlist 3 candidates, score them against the criteria, pick one and pin the exact commit or release. Record why the others were rejected. | Git, licence review, Ollama / NVIDIA / Gemini free tiers | Candidate agent repositories and licences | A selection record names the agent, its pinned version and licence, shows it was not written for TrustBench, and states that its core will not be modified beyond a documented adapter. | docs/external/agent-selection.md | No candidate supports tool calling on free models: fall back to a local model through Ollama, or document the gap and stop the phase before any claim. | Validation | TB-S1 |  |  | 0
TB-056 | 10 External agent validation | Define the external-agent threat model and integration contract | Not Started | TB-055 | TB-002 | Waiting | 4 |  |  | Map the external agent's trust boundaries: where prompts, tool outputs, memory and plugins enter. Decide which controls sit outside the agent (gateway, capability tokens, sandbox network policy) and which the agent cannot be trusted to enforce. Write the integration contract: tool names, argument schemas, error codes and trace fields the adapter must preserve. | Threat-model template from TB-002, docs/ | TB-002 threat model; external agent architecture docs | Contract and threat model reviewed against TB-002; every external entry point is classified as trusted or untrusted with the control that covers it, and any uncovered entry point is listed as out of scope. | docs/external/threat-model.md; docs/external/integration-contract.md | The agent has hidden tool paths (built-in browsing, shell, file access): disable them through configuration, or list them as uncovered and exclude them from claims. | Validation | TB-S1; TB-S2 |  |  | 0
TB-057 | 10 External agent validation | Build the external-agent adapter (TrustBench tools and the agent's own tool integration) | Not Started | TB-056 | TB-024 | Waiting | 12 |  |  | Mode A (controlled tools): expose the TrustBench tool services to the agent through its native tool interface (function tools or an MCP server), routed through the policy gateway. Mode B (native integration): keep at least one of the agent's own, independently implemented tool integrations (for example its SQL, HTTP-API or mail connector) unchanged, point it at a sandboxed local instance (database container or mock API server seeded with synthetic data, no real accounts), and interpose the gateway between that integration and its service without replacing the agent's tool environment. In both modes translate run configuration, model settings and step limits, and capture tool calls, final text and errors into the TrustBench trace schema. Keep the agent's own code unmodified. External agents are connected through the live website and API as well as locally: the run API reserves the agent field (external_mcp, langgraph_http, configs/live-service.yaml). | Agent SDK or MCP, src/gateway, TypeScript or Python adapter, Docker (sandboxed database or mock API) | Integration contract (TB-056); gateway and tool services; the agent's native tool integration and a synthetic sandbox instance for it | Mode A: adapter tests show every TrustBench tool callable from the agent and traces validating against the TB-004 schema. Mode B: at least one independently implemented native integration runs unchanged against its sandbox with every call passing through the gateway, which records an allow or deny decision per call; the sandbox holds synthetic data only. A diff proves no change to the agent's source or to the native integration's code. A connected external agent receives the same paired report through the website and trustbench remote. | src/external/; tests/external/adapter/; tests/external/native-integration/; docs/external/native-integration.md | The agent's tool interface cannot carry capability tokens: hold tokens in the adapter process, never in prompts, and enforce at the gateway. The native integration cannot be interposed (in-process client, pinned TLS): use a network-level proxy in the sandbox, or record Mode B as not demonstrated and limit claims to Mode A. | Validation | TB-S1 |  |  | 0
TB-058 | 10 External agent validation | Enforce tool authorization outside the agent | Not Started | TB-057 | TB-021 | Waiting | 6 |  |  | Run the agent in a sandbox whose only route to tools is the gateway (network egress denied, raw tool service unreachable). Bind each episode to a capability token held outside the agent. Add bypass tests: direct calls to tool services, forged or replayed tokens, unlisted tools, argument smuggling and calls after cancellation. Repeat the bypass tests against the Mode B native integration: its client must reach the sandboxed service only through the gateway. | Docker or a sandbox network policy, src/policy, pytest | TB-021 capability policy; TB-023 boundary tests | Every bypass test is refused and audited in both adapter modes (TrustBench tools and the native integration); a positive control proves each test can detect a working bypass; no tool effect occurs without a gateway allow decision in the audit log. | tests/external/authorization/; evidence/external-authorization-report.json | The agent framework makes network calls of its own (telemetry, model hub): allowlist only the model endpoint and record it. | Validation | TB-S2 |  |  | 0
TB-059 | 10 External agent validation | Map tasks and fixtures to the external agent | Not Started | TB-057 | TB-012 | Waiting | 5 |  |  | Deliver each benign task and attack fixture through the agent's native input (task prompt, documents as tool outputs). Keep fixtures, initial state and evaluators identical to the core benchmark; record any task the agent cannot express and why. | src/arms fixtures, src/evaluators, adapter | Development-split fixtures only (data/splits.json tuning groups) | Every development fixture either runs end to end with the unchanged evaluators or is listed with the reason it cannot; no holdout fixture is loaded (asserted by the runner). | docs/external/task-mapping.md; tests/external/fixtures/ | The agent rewrites or summarises tool outputs before acting, changing what an injection sees: record it as agent behaviour, not a fixture defect. | Validation | TB-S1 |  |  | 0
TB-060 | 10 External agent validation | Run conformance and smoke tests on the external agent | Not Started | TB-058 | TB-059 | Waiting | 4 |  |  | Run scripted (mock-model) conformance tests for the adapter, then a small live smoke run on the development split with both arms (agent alone, agent behind the gateway). Check traces, evaluator verdicts, spans and redaction end to end. Run the conformance and smoke checks through the live service as well. | Playwright or pytest, scripts/run-arm-smoke.mjs pattern, free models | Smoke suite (TB-012), adapter | Conformance suite passes; live smoke produces valid paired reports with complete evidence and no sensitive values in spans. | evidence/external-smoke-report.json; tests/external/conformance/ | Free-tier rate limits: pace requests and mark rate-limited runs invalid, never as results. | Validation | TB-S1 |  |  | 0
TB-061 | 10 External agent validation | Pre-register the external validation protocol and split procedure | Not Started | TB-060 | TB-006 | Waiting | 4 |  |  | Write an amendment before any external evaluation run: hypotheses, primary endpoints (unsafe committed-effect rate, benign utility), integration-overhead measures, adapter modes, repetitions, models, analysis and stopping rules. Register the split procedure, not the split: which fixture families are eligible (existing families never used in tuning, and families to be authored in TB-062), the seeded assignment rule to tuning or external validation, stratification, and the requirement that the sealed core holdout is excluded. Implement the procedure as a script and test it on placeholder family lists. | protocol/, scripts/verify-protocol.mjs | TB-006 protocol; experiment registry; inventory of existing fixture families and their tuning use | Amendment committed and verified before the first external evaluation run; the split script is committed with tests showing it is deterministic for its seed, excludes the core holdout and every tuning-used family, and refuses to reassign a family once assigned. | protocol/amendments.md (external validation entry); scripts/external-split.py; tests/external/split/ | The procedure is changed after families are seen: any change needs a new amendment committed before TB-062 assigns families. | Validation | TB-S1; TB-S2 |  |  | 0
TB-062 | 10 External agent validation | Build realistic adversarial scenarios | Not Started | TB-061 | TB-009 | Waiting | 8 |  |  | Author attack families closer to deployment: injections inside long realistic documents, tool-output injection across several tools, multi-step and delayed instructions, data exfiltration through allowed tools, and attacks on the agent's own planning or memory features. Each family has an oracle, a benign twin and a positive control. Then apply the TB-061 split procedure to the new and eligible existing families, write data/external-splits.json, and freeze the attack and split manifests with content hashes before any defended evaluation run. | data/ fixture builders, attack oracles, src/arms materialization | TB-009 fixtures; published attack patterns (cited) | Each family has a cited source or rationale, an oracle validated on scripted trajectories, a benign twin, and a split assigned by the registered TB-061 script; the split manifest is disjoint from the core holdout and the tuning families (checked by script) and its hash is committed before any defended run; positive controls succeed against the undefended agent. | data/external-attacks.jsonl; data/external-attack-oracles.json; data/external-splits.json; tests/external/attacks/ | Attacks tuned to defeat or to favour the gateway: freeze them before any defended run and report their source. Too few families for a meaningful external split: author more before assignment, never after. | Validation | TB-S1; TB-S2 |  |  | 0
TB-063 | 10 External agent validation | Test reliability and faults on the external agent | Not Started | TB-060 | TB-025 | Waiting | 5 |  |  | Inject tool timeouts, 5xx errors, malformed and oversized outputs, slow responses and cancellations through the adapter; check the agent's recovery, the gateway's replay safety and that no write is duplicated. Measure how often runs end at runtime limits. | TB-025 fault schedules, TB-026 durability, pytest | Fault profiles (tests/recovery/fault-schedules.json) | Every fault class is exercised; no duplicate committed write; termination and recovery rates reported per fault class with intervals. | evidence/external-reliability-report.json | The agent's own retry logic double-sends writes: rely on gateway idempotency keys and report the agent behaviour. | Validation | TB-S3 |  |  | 0
TB-064 | 10 External agent validation | Run the paired external evaluation | Not Started | TB-062 | TB-063 | Waiting | 10 |  |  | Run the external agent alone and behind the gateway on the external validation split, identical tasks, seeds, schedules and model revision, within the free-tier budget. Keep invalid, rate-limited and missing runs visible. | Batch runner, TB-028 schedules, free models | External validation split (data/external-splits.json, frozen in TB-062), frozen gateway configuration (configs/frozen/) | Paired reports for every scheduled unit or a recorded reason for each missing one; the provider revision is recorded and constant, or the comparison is labelled invalid. | runs/external/; evidence/external-*-report.json | Provider model changes mid-run: rerun both arms or label the comparison invalid. | Validation | TB-S1 |  |  | 0
TB-065 | 10 External agent validation | Measure security, utility and integration overhead | Not Started | TB-064 | TB-034 | Waiting | 5 |  |  | Compute the co-primary endpoints with cluster-bootstrap intervals, the false-block rate, latency and token overhead of the gateway path, and the integration cost (adapter size, agent configuration changes, unsupported features). Compare with the core results without pooling. | src/evaluation, TB-033/TB-034 analysis code | External paired reports | Metrics recomputed from raw records by script; every number links to its runs; integration overhead reported in measured units. | evidence/external-metrics.json; docs/external/results.md | Small samples: report intervals and refrain from claims the data cannot support. | Validation | TB-S1 |  |  | 0
TB-066 | 10 External agent validation | Report limitations and the integration guide | Not Started | TB-065 |  | Waiting | 5 |  |  | Write what transferred and what did not, negative results, uncovered entry points, the agent behaviours that weakened or strengthened the controls, and a step-by-step guide for wrapping another agent. Add the external results to the review site. Publish the external-agent path on the live website: a visitor connects an agent (LangGraph or a customer agent) and gets the report. | docs/, web/ | TB-065 results; TB-056 threat model | Limitations section lists every uncovered entry point and failed check; the guide is followed once on a clean checkout; claims stay within the measured scope. The live website guide is followed once with an external agent end to end. | docs/external/report.md; docs/external/integration-guide.md | Overgeneralising from one external agent: state the single-agent scope in every claim. | Validation | TB-S1; TB-S2 |  |  | 0
TB-067 | 11 Extensions | Evaluate another model family | Not Started | TB-066 |  | Waiting | 8 |  |  | Repeat paired evaluation with a second model under documented budgets. | Provider adapter | Same holdout tasks | Model-specific results and version differences are reported. | extensions/model-transfer/ | Additional API budget required. | Extension |  |  |  | 0
TB-068 | 11 Extensions | Explore adaptive policy selection | Not Started | TB-066 |  | Waiting | 12 |  |  | Learn or tune policy selection on tuning data and evaluate held-out utility/security tradeoffs. | Policy selector | Frozen baseline and tuning set | Improvement is assessed against a fixed-policy comparator. | extensions/adaptive-policy/ | Adaptation can create new attack paths. | Extension |  |  |  | 0
TB-069 | 11 Extensions | Test cross-session memory attacks | Not Started | TB-066 |  | Waiting | 8 |  |  | Add synthetic memory store and contamination fixtures with strict tenant boundaries. | Sandbox memory service | New attack-family holdout | Report memory-specific threat model and residual failures. | extensions/memory/ | Requires new labels and reset semantics. | Extension |  |  |  | 0
TB-070 | 11 Extensions | Measure attribution intervention quality | Not Started | TB-066 |  | Waiting | 10 |  |  | Remove or replace suspected faulty steps and test whether predicted fixes actually improve outcomes. | Controlled replay | Labeled trajectory failures | Intervention effects support or refute attribution claims. | extensions/causal-study/ | Counterfactual replay can alter downstream behavior. | Extension |  |  |  | 0
TB-071 | 11 Extensions | Run external reproduction review | Not Started | TB-066 |  | Waiting | 6 |  |  | Ask a reviewer to reproduce an allowed subset and document environment gaps. | Release artifact | Public quickstart | Reviewer report includes commands, versions and discrepancies. | extensions/reviewer-report.md | Reviewer time is a dependency, not guaranteed. | Extension |  |  |  | 0
TB-072 | 11 Extensions | Prepare submission candidate | Not Started | TB-067 | TB-071 | Waiting | 8 |  |  | Update literature, limitations and artifact checklist for a suitable venue after evidence review. | Report tooling | Validated extension findings | Claims remain consistent with experiments and related work. | extensions/submission/ | Submission is optional; acceptance and novelty are not promised. | Extension |  |  |  | 0
Phase dashboard
Phase | Tasks | Completed | Not Started | In Progress | Blocked | Complete % | Planned h | Remaining h | Ready
01 Scope & setup | 6 | 6 | 0 | 0 | 0 | 100% | 21 | 0 | 0
02 Data & fixtures | 6 | 6 | 0 | 0 | 0 | 100% | 24 | 0 | 0
03 Agent baseline | 6 | 6 | 0 | 0 | 0 | 100% | 27 | 0 | 0
04 Policy gateway | 6 | 6 | 0 | 0 | 0 | 100% | 33 | 0 | 0
05 Reliability & traces | 6 | 6 | 0 | 0 | 0 | 100% | 29 | 0 | 0
06 Evaluation | 6 | 6 | 0 | 0 | 0 | 100% | 33 | 0 | 0
07 Delivery & operations | 6 | 6 | 0 | 0 | 0 | 100% | 25 | 0 | 0
08 Research evidence | 6 | 6 | 0 | 0 | 0 | 100% | 25 | 0 | 0
09 Portfolio release | 6 | 1 | 5 | 0 | 0 | 16.67% | 16 | 13 | 1
10 External agent validation | 12 | 0 | 12 | 0 | 0 | 0% | 72 | 72 | 0
11 Extensions | 6 | 0 | 6 | 0 | 0 | 0% | 52 | 52 | 0
How to use and scope
| Purpose | Measure and improve agent task success, security and repeatability with an independently enforced tool boundary.
| Architecture | Test cases → agent adapter → policy gateway → sandbox tools → trace store → evaluators → regression gate.
| Build order | Work through phases 01–09 for Core. Phase 10 (External agent validation, Scope = Validation) follows the core roadmap and starts only after TB-054; phase 11 is optional. Dependencies refer to task IDs in this sheet; independent projects need no other project to be finished.
| Status and evidence | Use the status dropdown. Completed is a manual claim that every acceptance criterion passed. Paste the real report, commit or run URL in Actual evidence link. Expected evidence is a planned path, not a completed artifact.
| Readiness | Ready means both listed dependencies are marked Completed with evidence. Waiting means a prerequisite remains open. Bad dependency means an unknown/duplicate ID. Check prerequisites flags a task completed too early.
| Blocked work | Set Status to Blocked and record the reason plus next action in the final column. Readiness can still show Waiting if a dependency is unfinished. Unblock before continuing.
| Progress definition | Completion uses Completed task count, not subjective partial credit. Remaining hours subtract only completed tasks. Evidence gaps count completed tasks with an empty evidence field. Verify evidence quality manually.
| Effort and dates | Hours are rough active-work estimates, excluding unattended training, access waits and review delays. Edit estimates and hours/week. Core weeks left is remaining Core hours divided by capacity, not a promised calendar schedule. Enter your own due dates.
| Blank inputs | Owners, deadlines, actual evidence, blockers and benchmark measurements are intentionally blank. All project tasks begin Not Started. Research plans, targets and effort estimates are proposals, never measured achievements.
| Metric entries | Record baseline/candidate values only for matching units, splits and protocols. Delta is candidate minus baseline. Rates use one consistent decimal or percentage-point unit. Use the run link for intervals, counts and multi-value metrics.
| Acceptance versus improvement | A research task can finish with a null/negative result if protocol, analysis and evidence are complete. Production promotion must satisfy its own frozen gates. Do not invent improvements to mark a study complete.
| Workbook maintenance | This inventory has fixed bounded formulas. To add tasks, insert inside the inventory, update dashboard/readiness/phase ranges and validation as needed, and recheck counts. Do not insert a task into the source or metric tables.
| Master and standalone copies | Use the four-sheet master as the source of truth or choose a standalone copy. The workbooks do not synchronize. Avoid recording progress in multiple copies.
| Source freshness | Planning references checked on 14-Oct-2026. Main/latest docs can change. Pin versions during implementation and record access failures. A linked source supports tool/data choices, not novel performance claims.
| Research release | Deliver a literature matrix, preregistered protocol, raw run manifests, baselines, uncertainty, ablations, failure analysis and report. Publication acceptance, patentability and top-1-percent hiring outcomes are not promised.
Resources and hardware
| Compute route | CPU laptop and hosted model API are a viable starting route. Set an API budget before runs. A local GPU is optional and must be profiled for the chosen model; no fixed VRAM guarantee.
| Development kit | Git repository, Python environment, dependency lock, test runner, container runtime where supported, issue tracker and artifact directory. Pin exact versions after compatibility checks.
| Access and accounts | Core can begin locally. Create provider/model-host accounts only if the chosen route needs them. Verify model/dataset access, licenses, rate limits and current pricing before paid jobs.
| Data and experiment storage | Keep raw inputs immutable. Version derived datasets, split manifests, configs, seeds, logs and result tables. Use content hashes and retain failed runs.
| Budget control | Record actual rate, currency, token/GPU-hour budget and hard stop during the pilot. No dollar/rupee price is assumed in this workbook. Estimate cost from your measured workload.
| Optional complexity | Add graph databases, distributed queues, Kubernetes, multiple GPUs or new modalities only after a measured limitation justifies them. They are not prerequisites for the local core.
Dataset register
Data ID | Dataset | Purpose | Source IDs | Acquisition | Split / license / handling | Limitations
TB-D1 | AgentDojo selected suites | External evaluation | TB-S1 | Official repository at a pinned commit | Record license and exact suite/task IDs. Tune on separate families. | Benchmark may require provider credentials; label all subset results.
TB-D2 | Synthetic workflow fixtures | Development and policy invariants | TB-S1 | Locally generated documents, users, tools and expected state | No personal data. Version task templates and seed. | Ground truth comes from state checks, not a judge model.
TB-D3 | Local attack and failure fixtures | Robustness holdout | TB-S2 | Isolated injected documents, timeouts and malformed tool outputs | Split by attack/template family before tuning. | These measure only the defined threat model.
Evaluation register — measurements start blank
Record the unit and run link before comparing values. Delta = candidate − baseline; it is not automatically a pass/fail decision.
Metric ID | Metric | Definition / denominator | Better direction | Baseline value | Candidate value | Delta (formula) | Unit | Target (optional) | Run / evidence link | Protocol and acceptance guidance
TB-M1 | Benign task completion | Successful benign tasks / all eligible benign tasks | Higher | [6 empty] | State-based checker on paired held-out tasks. Set acceptable utility loss on tuning data before holdout.
TB-M2 | Attack success rate | Attacker goals achieved / all eligible attack trials | Lower | [6 empty] | Report per-family and overall with task-clustered intervals. Do not infer zero risk from zero observed attacks.
TB-M3 | False-block rate | Blocked permitted calls / all permitted attempted calls | Lower | [6 empty] | Use independently labeled permitted actions. Also report benign task completion to expose workflow impact.
TB-M4 | Repeated-run all-success | Tasks successful in every repeat / tasks with full repeat schedule | Higher | [6 empty] | Report repeat count, per-task frequency and missing-run count. Do not mix different repeat schedules.
TB-M5 | Attribution accuracy | Correct first-failure labels / reviewed labeled traces | Higher | [6 empty] | Human-adjudicated stratified trace sample. Judge output alone is insufficient ground truth.
TB-M6 | End-to-end p95 latency | 95th percentile of elapsed request-to-final-outcome seconds | Lower | [6 empty] | Same workload, concurrency, model and retries. Report timeouts separately and include queueing.
TB-M7 | Cost per successful task | Total billed currency across all attempts / successes | Lower | [6 empty] | Provider price date plus raw token/cost ledger. If successes are zero, report undefined rather than zero.
Research experiment inventory
Experiment ID | Research question | Comparators | Status | Config / run IDs | Result reference | Decision / finding | Compute used | Reviewer | Review date | Controls and analysis
T-E1 | Does gateway enforcement reduce attack success without excessive utility loss? | Baseline vs schema-only vs full gateway | Not Started | [6 empty] | Paired tasks, same model/settings and repeat schedule. Analysis: Task-clustered intervals and failure slices
T-E2 | Which enforcement layer contributes? | Remove provenance, capability checks or approval individually | Not Started | [6 empty] | Same frozen holdout and resource budgets. Analysis: Ablation effects and utility/cost tradeoff
T-E3 | Does recovery improve reliability under faults? | No retries vs bounded retries/checkpoints | Not Started | [6 empty] | Identical injected fault schedule. Analysis: Success, duplicates, latency and billed cost
T-E4 | Do trace diagnoses identify real causes? | Rule attribution vs reviewed labels; intervention as extension | Not Started | [6 empty] | Same labeled sample and blind review. Analysis: Accuracy plus limitations of causal interpretation
Project risks and mitigations
Risk ID | Risk | Trigger / concern | Owner | Status | Issue reference | Next action | Review effort h | Due | Evidence | Mitigation
TB-R1 | Threat-model coverage | Unknown attack families remain untested | [7 empty] | State supported surfaces and maintain new-family holdouts
TB-R2 | Provider variability | Model revisions or outages confound comparisons | [7 empty] | Capture version/time; pair runs and report incomplete trials
TB-R3 | Policy bypass | Raw client or alternate tool path bypasses gateway | [7 empty] | Centralize invocation and test every adapter
TB-R4 | Spend growth | Repeats, retries and attack variants multiply calls | [7 empty] | Pilot first, bound jobs and stop at budget
Sources and verification notes
Source ID | Primary reference | Use / verification limitation | Checked on | Pinned version | Local access result | License record | Config reference | Owner | Notes | Source URL
TB-S1 | AgentDojo repository | Benchmark setup, task/attack suites and license. Pin a commit. | 2026-10-14 | [6 empty] | https://github.com/ethz-spylab/agentdojo
TB-S2 | CaMeL: Defeating Prompt Injections by Design | Prior work on separating control and untrusted data. Compare scope; do not claim the idea as new. | 2026-10-14 | [6 empty] | https://arxiv.org/abs/2503.18813
TB-S3 | LangGraph interrupts | Durable pause/resume and node replay behavior for approval workflows. | 2026-10-14 | [6 empty] | https://docs.langchain.com/oss/python/langgraph/interrupts
Top: A1